## AO Dec. 2020
PHILIPPINE COCONUT AUTHORITY
CY 2019 COCONUT FERTILIZATION PROJECT
As of December, 2020
32658.5
REGION/ PROVINCE | Fertilizer Allocation (in bags) |  | VOLUME OF FERTILIZERS (in bags) | [5 empty] | VOLUME OF FERTILIZERS (in bags) | [5 empty] | AREA (in hectares |  | NO. OF TREES |  |  | NO. OF FARMER
|  |  | TOTAL SALT | [5 empty] | CCBOF | [7 empty] | Target | Applied | % | SALT | SALT + CCBOF | TOTAL
| TOTAL SALT | CCBOF/ Cocopeat | [6 empty] | (Salt + CCBOF) | [5 empty] | Target | Applied
|  |  | Delivered | % Delivered | Distributed | % Distributed | Applied | % Applied | Delivered | % Delivered | Distributed | % Distributed | Applied | % Applied
National | 276920 | 182103 | 200818 | 72.52% | 194710 | 70.31% | 185421 | 66.96% | 172903 | 94.95% | 140320 | 77.06% | 136485 | 74.95% | 70368.5 | 46951 | 7036850 | 4695100 | 66.72% | 33251 | 1996 | 35247
Luzon | 74678 | 31970 | 32468 | 43.48% | 28786 | 38.55% | 19976 | 26.75% | 22770 | 71.22% | 13190 | 41.26% | 11855 | 37.08% | 19808 | 5589.75 | 1980800 | 558975 | 28.22% | 1421 | 675 | 2096
Visayas | 38374 | 21333 | 21074 | 54.92% | 18648 | 48.6% | 18169 | 47.35% | 21333 | 100% | 8680 | 40.69% | 8680 | 40.69% | 9593.5 | 4542.25 | 959350 | 454225 | 47.35% | 4075 | 244 | 4319
Mindanao | 163868 | 128800 | 147276 | 89.87% | 147276 | 89.87% | 147276 | 89.87% | 128800 | 100% | 118450 | 91.96% | 115950 | 90.02% | 40967 | 36819 | 4096700 | 3681900 | 89.87% | 27755 | 1077 | 28832
I-IVB | 23369 | 0 | [12 empty] | 5842.25 |  | 584225
I | 360 | 0 | [12 empty] | 90 |  | 9000
Ilocos Norte | 180 | 0 | [12 empty] | 45 |  | 4500
Pangasinan | 180 | 0 | [12 empty] | 45 |  | 4500
II | 2330 | 0 | [12 empty] | 582.5 |  | 58250
Cagayan | 1440 | 0 | [12 empty] | 360 |  | 36000
Isabela | 260 | 0 | [12 empty] | 65 |  | 6500
Nueva Vizcaya | 260 | 0 | [12 empty] | 65 |  | 6500
Ifugao | 200 | 0 | [12 empty] | 50 |  | 5000
Quirino | 170 | 0 | [12 empty] | 42.5 |  | 4250
III | 3600 | 0 | [12 empty] | 900 |  | 90000
Bataan | 940 | 0 | [12 empty] | 235 |  | 23500
Aurora | 2660 | 0 | [12 empty] | 665 |  | 66500
IVB | 17079 | 0 | [12 empty] | 4269.75 |  | 426975
Marinduque | 2919 | 0 | [12 empty] | 729.75 |  | 72975
Oriental Mindoro | 2900 | [13 empty] | 725 |  | 72500
Occidental Mindoro | 1440 | 0 | [12 empty] | 360 |  | 36000
Romblon | 5500 | 0 | [12 empty] | 1375 |  | 137500
Palawan | 4320 | 0 | [12 empty] | 1080 |  | 108000
|  | 0 | [14 empty] | 0
IV-A | 32468 | 22770 | 32468 | 100% | 28786 | 88.66% | 19976 | 61.53% | 22770 | 100% | 13190 | 57.93% | 11855 | 52.06% | 9255.5 | 5589.75 | 925550 | 558975 |  | 1421 | 675 | 2096 | 499400 | 59275
Batangas | 5050 | 4060 | 5050 | 100% | 5050 | 100% | 5050 | 100% | 4060 | 100% | 4060 | 100% | 4060 | 100% | 1465.5 | 1465.5 | 146550 | 146550 |  | 346 | 217 | 563 | 150
Cavite | 1430 | 500 | 1430 | 100% | 1430 | 100% | 1430 | 100% | 500 | 100% | 500 | 100% | 500 | 100% | 382.5 | 382.5 | 38250 | 38250 |  | 119 | 37 | 156 | 78
Laguna | 5480 | 4100 | 5480 | 100% | 5322 | 97.12% | 5130 | 93.61% | 4100 | 100% | 4100 | 100% | 4100 | 100% | 1575 | 1487.5 | 157500 | 148750 |  | 418 | 287 | 705 | 205
Rizal | 1000 | 460 | 1000 | 100% | 980 | 98% | 868 | 86.8% | 460 | 100% | 460 | 100% | 460 | 100% | 273 | 240 | 27300 | 24000 |  | 42 | 31 | 73 | 23
Quezon I | 9752 | 6820 | 9752 | 100% | 8891 | 91.17% | 7250 | 74.34% | 6820 | 100% | 4070 | 59.68% | 2735 | 40.1% | 2779 | 1949.25 | 277900 | 194925 |  | 474 | 102 | 576 | 341
Quezon II | 9756 | 6830 | 9756 | 100% | 7113 | 72.91% | 248 | 2.542% | 6830 | 100% | 4777 | 69.94% | 60 | 0.8785% | 2780.5 | 65 | 278050 | 6500 |  | 22 | 1 | 23 | 341.5
|  | 0 | [14 empty] | 0
V | 18841 | 9200 | [12 empty] | 4710.25 |  | 471025 | [5 empty] | 460
Albay | 2561 | 0 | [12 empty] | 640.25 |  | 64025
Catanduanes | 1000 | 0 | [12 empty] | 250 |  | 25000
Camarines Norte | 2000 | 0 | [12 empty] | 500 |  | 50000
Camarines Sur I | 2000 | 0 | [12 empty] | 500 |  | 50000
Camarines Sur II | 5120 | 0 | [12 empty] | 1280 |  | 128000
Masbate | 4160 | 9200 | [12 empty] | 1040 |  | 104000 | [5 empty] | 460
Sorsogon | 2000 | 0 | [12 empty] | 500 |  | 50000
|  | 0 | [14 empty] | 0
VI | 7274 | 3680 | 7274 | 100% | 6042 | 83.06% | 6042 | 83.06% | 3680 | 100% | 3680 | 100% | 3680 | 100% | 1818.5 | 1510.5 | 181850 | 151050 |  | 1943 |  | 1943 | 230
Aklan | 1370 | 1200 | 1370 | 100% | 1370 | 100% | 1370 | 100% | 1200 | 100% | 1200 | 100% | 1200 | 100% | 342.5 | 342.5 | 34250 | 34250 |  | 404 |  | 404 | 75
Antique | 600 | 400 | 600 | 100% | 363 | 60.5% | 363 | 60.5% | 400 | 100% | 400 | 100% | 400 | 100% | 150 | 90.75 | 15000 | 9075 |  | 122 |  | 122 | 25
Capiz | 1650 | 640 | 1650 | 100% | 1650 | 100% | 1650 | 100% | 640 | 100% | 640 | 100% | 640 | 100% | 412.5 | 412.5 | 41250 | 41250 |  | 524 |  | 524 | 40
Guimaras | 704 | 160 | 704 | 100% | 704 | 100% | 704 | 100% | 160 | 100% | 160 | 100% | 160 | 100% | 176 | 176 | 17600 | 17600 |  | 268 |  | 268 | 10
Iloilo | 1300 | 640 | 1300 | 100% | 305 | 23.46% | 305 | 23.46% | 640 | 100% | 640 | 100% | 640 | 100% | 325 | 76.25 | 32500 | 7625 |  | 101 |  | 101 | 40
Negros Occidental | 1650 | 640 | 1650 | 100% | 1650 | 100% | 1650 | 100% | 640 | 100% | 640 | 100% | 640 | 100% | 412.5 | 412.5 | 41250 | 41250 |  | 524 |  | 524 | 40
|  | 0 | [14 empty] | 0
VII | 13800 | 17653 | 13800 | 100% | 12606 | 91.35% | 12127 | 87.88% | 17653 | 100% | 5000 | 28.32% | 5000 | 28.32% | 3450 | 3031.75 | 345000 | 303175 |  | 2132 | 244 | 2376 | 882.65
Bohol | 4000 | 5000 | 4000 | 100% | 4000 | 100% | 4000 | 100% | 5000 | 100% | 5000 | 100% | 5000 | 100% | 1000 | 1000 | 100000 | 100000 |  | 633 | 244 | 877 | 250
Cebu | 4000 | 5000 | 4000 | 100% | 2946 | 73.65% | 2928 | 73.2% | 5000 | 100% |  | 0% |  | 0% | 1000 | 732 | 100000 | 73200 |  | 487 |  | 487 | 250
Negros Oriental | 4800 | 7653 | 4800 | 100% | 4660 | 97.08% | 4199 | 87.48% | 7653 | 100% |  | 0% |  | 0% | 1200 | 1049.75 | 120000 | 104975 |  | 774 |  | 774 | 382.65
Siquijor | 1000 | 0 | 1000 | 100% | 1000 | 100% | 1000 | 100% |  | #DIV/0! |  |  |  |  | 250 | 250 | 25000 | 25000 |  | 238 |  | 238
|  | 0 | [14 empty] | 0
VIII | 17300 | 0 | [12 empty] | 4325 |  | 432500
Leyte 1 | 2076 | 0 | [12 empty] | 519 |  | 51900
Northwestern Leyte | 2595 | 0 | [12 empty] | 648.75 |  | 64875
Biliran | 346 | 0 | [12 empty] | 86.5 |  | 8650
Southern Leyte | 1903 | 0 | [12 empty] | 475.75 |  | 47575
Samar | 3460 | 0 | [12 empty] | 865 |  | 86500
Eastern Samar | 3287 | 0 | [12 empty] | 821.75 |  | 82175
Northern Samar | 3633 | 0 | [12 empty] | 908.25 |  | 90825
0
IX | 20388 | 23000 | 20388 | 100% | 20388 | 100% | 20388 | 100% | 23000 | 100% | 23000 | 100% | 23000 | 100% | 5097 | 5097 | 509700 | 509700 |  | 3078 | 1077 | 4155 | 1150
Zamboanga del Norte | 9292 | 8400 | 9292 | 100% | 9292 | 100% | 9292 | 100% | 8400 | 100% | 8400 | 100% | 8400 | 100% | 2323 | 2323 | 232300 | 232300 |  | 1102 | 384 | 1486 | 400
Zamboanga del Sur | 8116 | 6000 | 8116 | 100% | 8116 | 100% | 8116 | 100% | 6000 | 100% | 6000 | 100% | 6000 | 100% | 2029 | 2029 | 202900 | 202900 |  | 1351 | 277 | 1628 | 300
Zamboanga Sibugay | 2260 | 5000 | 2260 | 100% | 2260 | 100% | 2260 | 100% | 5000 | 100% | 5000 | 100% | 5000 | 100% | 565 | 565 | 56500 | 56500 |  | 455 | 236 | 691 | 250
Zamboanga City | 720 | 3600 | 720 | 100% | 720 | 100% | 720 | 100% | 3600 | 100% | 3600 | 100% | 3600 | 100% | 180 | 180 | 18000 | 18000 |  | 170 | 180 | 350 | 200
|  | 0 | [13 empty] | 0 | 0 | 0
|  | 0 | [13 empty] | 0 | 0 | 0
X | 36704 | 0 | 36704 | 100% | 36704 | 100% | 36704 | 100% | [6 empty] | 9176 | 9176 | 917600 | 917600 |  | 5332 | 0 | 5332
Bukidnon | 9324 | 0 | 9324 | 100% | 9324 | 100% | 9324 | 100% | [6 empty] | 2331 | 2331 | 233100 | 233100 |  | 2400 |  | 2400
Camiguin | 144 | 0 | 144 | 100% | 144 | 100% | 144 | 100% | [6 empty] | 36 | 36 | 3600 | 3600 |  | 28 |  | 28
Lanao del Norte | 7308 | 0 | 7308 | 100% | 7308 | 100% | 7308 | 100% | [6 empty] | 1827 | 1827 | 182700 | 182700 |  | 1212 |  | 1212
Misamis Occidental | 7728 | 0 | 7728 | 100% | 7728 | 100% | 7728 | 100% | [6 empty] | 1932 | 1932 | 193200 | 193200 |  | 752 |  | 752
Misamis Oriental | 12200 | 0 | 12200 | 100% | 12200 | 100% | 12200 | 100% | [6 empty] | 3050 | 3050 | 305000 | 305000 |  | 940 |  | 940
|  | 0 | [13 empty] | 0 | 0 | 0
XI | 34960 | 0 | 34960 | 100% | 34960 | 100% | 34960 | 100% | [6 empty] | 8740 | 8740 | 874000 | 874000 |  | 9853 | 0 | 9853
Davao City | 5822 | 0 | 5822 | 100% | 5822 | 100% | 5822 | 100% | [6 empty] | 1455.5 | 1455.5 | 145550 | 145550 |  | 1525 |  | 1525
Davao del Sur | 7896 | 0 | 7896 | 100% | 7896 | 100% | 7896 | 100% | [6 empty] | 1974 | 1974 | 197400 | 197400 |  | 2260 |  | 2260
Davao Occidental | 3754 | 0 | 3754 | 100% | 3754 | 100% | 3754 | 100% | [6 empty] | 938.5 | 938.5 | 93850 | 93850 |  | 942 |  | 942
Davao del Norte | 5824 | 0 | 5824 | 100% | 5824 | 100% | 5824 | 100% | [6 empty] | 1456.5 | 1456 | 145650 | 145600 |  | 1697 |  | 1697
Compostela Valley | 5824 | 0 | 5824 | 100% | 5824 | 100% | 5824 | 100% | [6 empty] | 1455.5 | 1456 | 145550 | 145600 |  | 1891 |  | 1891
Davao Oriental | 5840 | 0 | 5840 | 100% | 5840 | 100% | 5840 | 100% | [6 empty] | 1460 | 1460 | 146000 | 146000 |  | 1538 |  | 1538
|  | 0 | [13 empty] | 0 | 0 | 0
XII | 34160 | 0 | 34160 | 100% | 34160 | 100% | 34160 | 100% | [6 empty] | 8540 | 8540 | 854000 | 854000 |  | 6384 |  | 6384
North Cotabato | 9360 | 0 | 9360 | 100% | 9360 | 100% | 9360 | 100% | [6 empty] | 2340 | 2340 | 234000 | 234000 |  | 1745 |  | 1745
Saranggani | 8800 | 0 | 8800 | 100% | 8800 | 100% | 8800 | 100% | [6 empty] | 2200 | 2200 | 220000 | 220000 |  | 1424 |  | 1424
South Cotabato | 8000 | 0 | 8000 | 100% | 8000 | 100% | 8000 | 100% | [6 empty] | 2000 | 2000 | 200000 | 200000 |  | 1321 |  | 1321
Sultan Kudarat | 8000 | 0 | 8000 | 100% | 8000 | 100% | 8000 | 100% | [6 empty] | 2000 | 2000 | 200000 | 200000 |  | 1894 |  | 1894
|  | 0 | [13 empty] | 0 | 0 | 0
CARAGA | 16592 | 46000 | 0 | 0% |  |  |  |  | 46000 | 100% | 35650 | 77.5% | 33150 | 72.07% | 4148 | 0 | 414800 | 0 |  | 2329 |  | 2329 | 2300
Agusan del Norte | 3640 | 9200 |  | 0% |  |  |  |  | 9200 | 100% | 9200 | 100% | 9200 | 100% | 910 | 0 | 91000 | 0 |  | 483 |  | 483 | 460
Agusan del Sur | 4532 | 9200 |  | 0% |  |  |  |  | 9200 | 100% | 9200 | 100% | 9200 | 100% | 1133 | 0 | 113300 | 0 |  | 870 |  | 870 | 460
Surigao del Sur | 3840 | 9200 |  | 0% |  |  |  |  | 9200 | 100% | 8060 | 87.61% | 8060 | 87.61% | 960 | 0 | 96000 | 0 |  | 664 |  | 664 | 460
Surigao del Norte | 2740 | 9200 |  | 0% |  |  |  |  | 9200 | 100% | 7850 | 85.33% | 5350 | 58.15% | 685 | 0 | 68500 | 0 |  | 198 |  | 198 | 460
Dinagat Islands | 1840 | 9200 |  | 0% |  |  |  |  | 9200 | 100% | 1340 | 14.57% | 1340 | 14.57% | 460 | 0 | 46000 | 0 |  | 114 |  | 114 | 460
[16 empty] | 0 | 0 | 0
ARMM | 21064 | 59800 | 21064 | 100% | 21064 | 100% | 21064 | 100% | 59800 | 100% | 59800 | 100% | 59800 | 100% | 5266 | 5266 | 526600 | 526600 |  | 779 |  | 779
Basilan | 2278 |  | 2278 | 100% | 2278 | 100% | 2278 | 100% |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | 569.5 | 569.5 | 56950 | 56950 |  | 43 |  | 43
Lanao del Sur | 5998 | 23800 | 5998 | 100% | 5998 | 100% | 5998 | 100% | 23800 | 100% | 23800 | 100% | 23800 | 100% | 1499.5 | 1499.5 | 149950 | 149950 |  | 426 |  | 426
Maguindanao | 7938 | 30000 | 7938 | 100% | 7938 | 100% | 7938 | 100% | 30000 | 100% | 30000 | 100% | 30000 | 100% | 1984.5 | 1984.5 | 198450 | 198450 |  | 27 |  | 27
Sulu | 2400 |  | 2400 | 100% | 2400 | 100% | 2400 | 100% |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | 600 | 600 | 60000 | 60000 |  | 135 |  | 135
Tawi-Tawi | 2450 | 6000 | 2450 | 100% | 2450 | 100% | 2450 | 100% | 6000 | 100% | 6000 | 100% | 6000 | 100% | 612.5 | 612.5 | 61250 | 61250 |  | 148 |  | 148